## Cover Sheet
ASSIGNMENT 1
DO INITIAL VERSION OF PERSONAL WBS
CSE 6329
Software Metrics and Quality Engineering
Fall, 2019
Name | Goutami Padmanabhan
ID | 1001669338
Points
(/10) Correct Format, including name on top, totals, etc.
(/50) Reasonable list of tasks for each assignment
(/40) Reasonable estimates, actual and earned hours.
(100) Total Assignment Grade
Comments from Grader
Note: | If you receive comments on the DRAFT PWBS, make the indicated changes and delete the
comments when submitting the INTERIM PWBS.
If you receive comments on the INTERIM PWBS, delete them before submitting the FINAL PWBS.
1

## Instructions
Instructions for Setting Up the WBS and Making Weekly WBS Entries
General Rules:
1: Cells with a white background are cells in which you may put a number or a task name at the appropriate time.
Some of these cells will change color when you put something there.
2: Row 7/8 contains the headers for the many rows that follow. These row headers are color coded:
|  | If a cell has a header that is |  |  |  | light blue | it means you should consider entering data in that column each week.
|  | If a cell has a header that is |  |  |  | beige | it means you should enter data there once and not change it later.
|  | If a cell has a header that is |  |  |  | light green | it means you should enter task numbers and names there once.
|  | If a cell has a header that is |  |  |  | yellow | it means it contains a formula that you should not change.
Note: you must add new rows in the main body of the WBS (see SOW for details)
3: Cells with a colored background usually contain formulas that you should not change unless you are extending
the length of the course (which you may only do with the instructor's permission).
However, if you add new rows, check that all formulas are correct (compare with nearby rows)
4: You may insert rows as needed to accommodate all of the tasks that you plan to do for the course.
(Use the spare tasks near the bottom to preserve the correct format and formulas.)
5: You should study every formula and every graph and understand what it is and why. This may be on an exam.
What to do after you have created all of your task rows and estimated the hours of effort for each task.
Step 1 - Enter hours worked each week
At the end of each week, fill in hours worked on each task, as follows:
(hours may be entered in whole hours, such as 2, or in tenths of an hour, such as 1.3)
For each task:
If you did no work on that task, do nothing.
If you worked on that task during the past week:
Enter total hours worked on the task in the column corresponding to the current week (column S through AF).
Cell should change color when you enter a non-zero value.
Enter total hours of work remaining on the task in column E:
If the task is complete, enter 0 hours remaining.
The total hours remaining is your best current estimate, which may differ from what was originally estimated.
Thus this value may change each week.
Step 2: Check for errors
Review all totals and numbers and make sure everything seems correct.
Make corrections as necessary
If the graphs (charts) look strange, something is wrong. Figure out what's wrong and fix it.
Step 3: Record Estimated Hours Remaining at end of current week
Copy the "total estimated hours remaining" (bottom of column E) to estimated hours remaining cell for current week
Copy the value, not the formula. I.e., don't just copy. Use copy / paste special / values
Cell will change color
This will update the burndown and burnup charts
Step 4: Update Earned Value
See the SOW and below for how to compute the earned value each week. Be sure to do this exactly as described.
The earned value for each week goes in the hours earned this week row for the current week (near the bottom)
Here is how to compute the earned value each week:
Set the hours earned this week to 0 (I suggest you do this on scratch paper, not in the spreadsheet)
If you did not complete any tasks this week, your earned value for the week is 0.
For each task that you completed during the current week:
Find the originally estimated hours for that task and add it to the hours earned this week
Repeat for the next completed task until you have done this for all tasks that were completed this week
(Do not include tasks that you did not complete this week.)
When you have added the originally estimated hours for all the completed tasks, this total will be the earned value for the week.
Place the earned value for the week in the hours earned this week row. This will update the earned value chart accordingly.

## WBS
|  | PWBS | [6 empty] | Planned Effort |  | 10.9286 | 10.9286 | 10.9286 | 10.9286 | 10.9286 | 10.9286 | 10.9286 | 10.9286 | 10.9286 | 10.9286 | 10.9286 | 10.9286 | 10.9286 | 10.9286 |  | 153
Not Started | 2019 Fall | CSE 6329-002 | [6 empty] | Cumulative Plan (PV) |  | 10.9286 | 21.8571 | 32.7857 | 43.7143 | 54.6429 | 65.5714 | 76.5 | 87.4286 | 98.3571 | 109.2857 | 120.2143 | 131.1429 | 142.0714 | 153
In Progress | Goutami Padmanabhan | [7 empty] | Estimated Effort Remaining | 153 | 142.0714 | 131.1429 | 120.2143 | 109.2857 | 98.3571 | 87.4286 | 76.5 | 65.5714 | 54.6429 | 43.7143 | 32.7857 | 21.8571 | 10.9286 | -1.7764e-14
Complete | Actual Results |  | Estimates | WBS | [6 empty] | Actual Hours Worked and Earned
Status |  | Actual Hours So Far |  | Task # | Task Description |  |  |  | Week Ending >> |  | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14
| Estimated Hours Remaining | Actual Hours So Far | Estimated Hours of Effort | [5 empty] | Week Ending >> |  | 2019-08-30 | 2019-09-06 | 2019-09-13 | 2019-09-20 | 2019-09-27 | 2019-10-04 | 2019-10-11 | 2019-10-18 | 2019-10-25 | 2019-11-01 | 2019-11-08 | 2019-11-15 | 2019-11-22 | 2019-11-29 | insert new column here | Total Hours Worked
|  |  |  | 10000 | A1 - Develop PWBS
|  |  |  | 11000 |  | Read and Analyze A1 SOW for PWBS
Complete | 0 | 1.5 | 1 | 11100 |  |  | List tasks to be performed |  |  |  | 2019-08-30: 1.5 |  | 1.5
Complete | 0 | 0.2 | 0.6 | 11200 |  |  | Estimate hours required for each task |  |  |  | 2019-08-30: 0.2 |  | 0.2
Complete | 0 | 1 | 1 | 11300 |  |  | Break into smaller sub-tasks as required | [18 empty] | 1 | bar: 2019-08-30
Complete | 0 | 0.7 | 0.8 | 11400 |  |  | Modify template to add tasks and correct formulas/coloring |  |  |  | 2019-08-30: 0.7 |  | 0.7
Complete | 0 | 0.3 | 0.4 | 11500 |  |  | Record estimated hours in Estimated Hours of Effort column |  |  |  | 2019-08-30: 0.3 |  | 0.3
|  |  |  | 12000 |  | Read and Analyze A2 SOW
Complete | 0 | 1.2 | 1 | 12100 |  |  | List tasks to be performed |  |  |  | 2019-08-30: 1.2 |  | 1.2
Complete | 0 | 0.2 | 0.6 | 12200 |  |  | Estimate hours required for each task |  |  |  | 2019-08-30: 0.2 |  | 0.2
Complete | 0 | 1 | 1 | 12300 |  |  | Break into smaller sub-tasks as required | [18 empty] | 1 | bar: 2019-08-30
Complete | 0 | 0.7 | 0.8 | 12400 |  |  | Modify template to add tasks and correct formulas/coloring |  |  |  | 2019-08-30: 0.7 |  | 0.7
Complete | 0 | 0.5 | 0.8 | 12500 |  |  | Record estimated hours in Estimated Hours of Effort column |  |  |  | 2019-08-30: 0.5 |  | 0.5
|  |  |  | 13000 |  | Read and Analyze A3 SOW
Complete | 0 | 1.2 | 1 | 13100 |  |  | List tasks to be performed |  |  |  | 2019-08-30: 1.2 |  | 1.2
Complete | 0 | 0.2 | 0.6 | 13200 |  |  | Estimate hours required for each task |  |  |  | 2019-08-30: 0.2 |  | 0.2
Complete | 0 | 1 | 0.9 | 13300 |  |  | Break into smaller sub-tasks as required | [18 empty] | 1 | bar: 2019-08-30
Complete | 0 | 0.2 | 0.5 | 13400 |  |  | Modify template to add tasks and correct formulas/coloring |  |  |  | 2019-08-30: 0.2 |  | 0.2
Complete | 0 | 0.2 | 0.5 | 13500 |  |  | Record estimated hours in Estimated Hours of Effort column |  |  |  | 2019-08-30: 0.2 |  | 0.2
|  |  |  | 14000 |  | Read and Analyze A4 SOW
Complete | 0 | 1 | 1 | 14100 |  |  | List tasks to be performed | [18 empty] | 1 | bar: 2019-08-30
Complete | 0 | 0.5 | 0.4 | 14200 |  |  | Estimate hours required for each task |  |  |  | 2019-08-30: 0.5 |  | 0.5
Complete | 0 | 0.5 | 0.9 | 14300 |  |  | Break into smaller sub-tasks as required |  |  |  | 2019-08-30: 0.5 |  | 0.5
Complete | 0 | 0.8 | 0.4 | 14400 |  |  | Modify template to add tasks and correct formulas/coloring |  |  |  | 2019-08-30: 0.8 |  | 0.8
Complete | 0 | 0.5 | 0.5 | 14500 |  |  | Record estimated hours in Estimated Hours of Effort column |  |  |  | 2019-08-30: 0.5 |  | 0.5
Complete | 0 | 0.2 | 0.5 | 15000 |  | Enter Actual and Earned Hours for week ending 8/30 |  |  |  |  | 2019-08-30: 0.2 |  | 0.2
Complete | 0 | 0.5 | 0.5 | 15100 |  | Submit A1 (Draft) |  |  |  |  | 2019-08-30: 0.5 |  | 0.5
Not Started | 1.5 | 0 | 1.5 | 16000 |  | Review comments from TA/Instructor and Correct Mistakes | [19 empty] | 0
|  |  |  | 17000 |  | Make Weekly Updates to Actual and Earned Hours in PWBS
Complete | 0 | 1 | 1.2 | 17100 |  |  | Record hours worked for week ending |  | 2019-08-30 | [16 empty] | 1 | bar: 2019-08-30
Not Started | 1.2 | 0 | 1.2 | 17200 |  |  | Record hours worked for week ending |  | 2019-09-06 | [16 empty] | 0
Not Started | 1.2 | 0 | 1.2 | 17300 |  |  | Record hours worked for week ending |  | 2019-09-13 | [16 empty] | 0
Not Started | 1.2 | 0 | 1.2 | 17400 |  |  | Record hours worked for week ending |  | 2019-09-20 | [16 empty] | 0
Not Started | 1.2 | 0 | 1.2 | 17500 |  |  | Record hours worked for week ending |  | 2019-09-27 | [16 empty] | 0
Not Started | 1.2 | 0 | 1.2 | 17600 |  |  | Record hours worked for week ending |  | 2019-10-04 | [16 empty] | 0
Not Started | 1.2 | 0 | 1.2 | 17700 |  |  | Record hours worked for week ending |  | 2019-10-11 | [16 empty] | 0
Not Started | 1.2 | 0 | 1.2 | 17800 |  |  | Record hours worked for week ending |  | 2019-10-18 | [16 empty] | 0
Not Started | 1.2 | 0 | 1.2 | 17900 |  |  | Record hours worked for week ending |  | 2019-10-25 | [16 empty] | 0
Not Started | 1.2 | 0 | 1.2 | 17910 |  |  | Record hours worked for week ending |  | 2019-11-01 | [16 empty] | 0
Not Started | 1.2 | 0 | 1.2 | 17920 |  |  | Record hours worked for week ending |  | 2019-11-08 | [16 empty] | 0
Not Started | 1.2 | 0 | 1.2 | 17930 |  |  | Record hours worked for week ending |  | 2019-11-15 | [16 empty] | 0
Not Started | 1.2 | 0 | 1.2 | 17940 |  |  | Record hours worked for week ending |  | 2019-11-22 | [16 empty] | 0
Not Started | 1.2 | 0 | 1.2 | 17940 |  |  | Record hours worked for week ending |  | 2019-11-29 | [16 empty] | 0
Not Started | 1 | 0 | 1 | 18000 |  | Submit Final PWBS | [19 empty] | 0
|  |  |  | 20000 | A2
|  |  |  | 21000 |  | Recording and Analysis DRAT Tool
Not Started | 1 | 0 | 1 | 21100 |  |  | Record the defect data | [18 empty] | 0
|  |  |  | 21200 |  |  | Refinement and analysis of the data
Not Started | 1.3 | 0 | 1.3 | 21210 |  |  |  | Shifting and sorting the data | [17 empty] | 0
Not Started | 1 | 0 | 1 | 21220 |  |  |  | Extracting subsets of the data | [17 empty] | 0
Not Started | 1.3 | 0 | 1.3 | 21230 |  |  |  | Computing totals, averages and other measures | [17 empty] | 0
|  |  |  | 21300 |  |  | Generate various graphs
Not Started | 0.9 | 0 | 0.9 | 21310 |  |  |  | Post-release Quality Average Normalized by Size | [17 empty] | 0
Not Started | 0.9 | 0 | 0.9 | 21320 |  |  |  | Post-release Quality by Development Process | [17 empty] | 0
Not Started | 0.9 | 0 | 0.9 | 21330 |  |  |  | Post-release Quality by Programming Language | [17 empty] | 0
Not Started | 0.9 | 0 | 0.9 | 21340 |  |  |  | Post-release Quality History | [17 empty] | 0
Not Started | 0.7 | 0 | 0.7 | 21350 |  |  |  | Current Quality Total | [17 empty] | 0
Not Started | 0.7 | 0 | 0.7 | 21360 |  |  |  | Current Quality Total Normalized by Size | [17 empty] | 0
Not Started | 0.7 | 0 | 0.7 | 21370 |  |  |  | Current Quality Total Normalized by Number of Products | [17 empty] | 0
|  |  |  | 22000 |  | Documentation
|  |  |  | 22100 |  |  | Prepare a Defect Analysis Report
Not Started | 1.6 | 0 | 1.6 | 22110 |  |  |  | Analysis Tool Description | [17 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 22120 |  |  |  | Individual Measure and Graph Descriptions | [17 empty] | 0
Not Started | 0.8 | 0 | 0.8 | 22130 |  |  |  | Summary and Recommendations | [17 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 23000 |  | Review the assignment A2 and resolve issues | [19 empty] | 0
Not Started | 0.5 | 0 | 0.5 | 24000 |  | Submit A2 | [19 empty] | 0
|  |  |  | 30000 | A3
|  |  |  | 31000 |  | Phase 1
|  |  |  | 31100 |  |  | Main Program
Not Started | 1.5 | 0 | 1.5 | 99910 |  |  |  | Produce a flowgraph of the main program | [17 empty] | 0
Not Started | 1 | 0 | 1 | 99910 |  |  |  | Compute the cyclomatic complexity of the main program | [17 empty] | 0
|  |  |  | 31200 |  |  | Function
Not Started | 1.6 | 0 | 1.6 | 99910 |  |  |  | Write a C function | [17 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 99910 |  |  |  | Produce a flowgraph of the function | [17 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 99910 |  |  |  | Compute the cyclomatic complexity of the function | [17 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 31300 |  |  | Review the assignment A3 Phase1 and resolve issues | [18 empty] | 0
Not Started | 0.5 | 0 | 0.5 | 31400 |  |  | Submit A3 Phase 1 | [18 empty] | 0
|  |  |  | 32000 |  | Phase 2
|  |  |  | 32100 |  |  | Review and evaluate each of three programs
Not Started | 0.8 | 0 | 0.8 | 32110 |  |  |  | Review the function and evaluate any errors | [17 empty] | 0
Not Started | 1.8 | 0 | 1.8 | 32120 |  |  |  | Produce a flowgraph | [17 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 32130 |  |  |  | Compute the cyclomatic complexity | [17 empty] | 0
|  |  |  | 32200 |  |  | Prepare a report in Word document
Not Started | 0.5 | 0 | 0.5 | 32210 |  |  |  | File Name of the function | [17 empty] | 0
Not Started | 0.5 | 0 | 0.5 | 32220 |  |  |  | Describe errors and explain correction | [17 empty] | 0
Not Started | 0.5 | 0 | 0.5 | 32230 |  |  |  | Calculating cyclomatic complexity | [17 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 32300 |  |  | Review the assignment A3 Phase 2 and resolve issues | [18 empty] | 0
Not Started | 0.5 | 0 | 0.5 | 32400 |  |  | Submit A3 Phase 2 | [18 empty] | 0
|  |  |  | 40000 | A4
|  |  |  | 41000 |  | Define
Not Started | 1 | 0 | 1 | 41100 |  |  | Identify two CTQs | [18 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 41200 |  |  | Explain the measure for base and compound measures | [18 empty] | 0
|  |  |  | 42000 |  | Measure
|  |  |  | 42100 |  |  | Describe the process flow using a swim lane diagram
Not Started | 1.8 | 0 | 1.8 | 42110 |  |  |  | Examine all handouts to identify the people involved | [17 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 42120 |  |  |  | Produce a simple table of people and organizations | [17 empty] | 0
Not Started | 0.8 | 0 | 0.8 | 42130 |  |  |  | Determine the order of processes | [17 empty] | 0
Not Started | 0.8 | 0 | 0.8 | 42140 |  |  |  | Determine the dependencies | [17 empty] | 0
Not Started | 1 | 0 | 1 | 42150 |  |  |  | Produce a swim lane diagram | [17 empty] | 0
Not Started | 0.8 | 0 | 0.8 | 42160 |  |  |  | Examine the swim lane diagram and the IPC information | [17 empty] | 0
|  |  |  | 43000 |  | ANALYZE - slow response problem
Not Started | 1.5 | 0 | 1.5 | 43100 |  |  | Analyze root causes of the customer’s slow response time problem | [18 empty] | 0
Not Started | 0.8 | 0 | 0.8 | 43200 |  |  | Produce a Summary of Causes table | [18 empty] | 0
Not Started | 0.8 | 0 | 0.8 | 43300 |  |  | Produce a cause map (causal model) | [18 empty] | 0
|  |  |  | 44000 |  | ANALYZE - high defect rate problem
|  |  |  | 44100 |  |  | Determine causes of the high defect rate problem
Not Started | 1 | 0 | 1 | 44110 |  |  |  | Phase 1 - identify relationships between defect level and factors | [17 empty] | 0
Not Started | 1 | 0 | 1 | 44120 |  |  |  | Phase 2 - identify correlations | [17 empty] | 0
Not Started | 1 | 0 | 1 | 44130 |  |  |  | Phase 3 - Produce a cause map (causal model) | [17 empty] | 0
|  |  |  | 45000 |  | IMPROVE
|  |  |  | 99900 |  |  | Produce a Table of Most Important Root Causes
Not Started | 0.8 | 0 | 0.7 | 44130 |  |  |  | Identify the overall root causes | [17 empty] | 0
Not Started | 1 | 0 | 1 | 44130 |  |  |  | Explain root causes | [17 empty] | 0
Not Started | 0.8 | 0 | 0.8 | 45200 |  |  | Explain the Recommended Solutions | [18 empty] | 0
Not Started | 1.8 | 0 | 1.8 | 91000 |  | Review the assignment A4 and resolve issues | [19 empty] | 0
Not Started | 0.5 | 0 | 0.5 | 91000 |  | Submit A4 | [19 empty] | 0
|  |  |  | 50000 | E1 - Study for Midterm Exam
Not Started | 1 | 0 | 1 | 51000 |  | Time-table plan to study for Midterm Exam | [19 empty] | 0
|  |  |  | 52000 |  | Study Modules 1-5
Not Started | 1.5 | 0 | 1.5 | 52100 |  |  | Study Module 1 | [18 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 52200 |  |  | Study Module 2 | [18 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 52300 |  |  | Study Module 3 | [18 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 52400 |  |  | Study Module 4 | [18 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 52500 |  |  | Study Module 5 | [18 empty] | 0
|  |  |  | 53000 |  | Study Modules 6-10
Not Started | 1.5 | 0 | 1.5 | 53100 |  |  | Study Module 6 | [18 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 53200 |  |  | Study Module 7 | [18 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 53300 |  |  | Study Module 8 | [18 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 53400 |  |  | Study Module 9 | [18 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 53500 |  |  | Study Module 10 | [18 empty] | 0
|  |  |  | 54000 |  | Study Modules 11-15
Not Started | 1.5 | 0 | 1.5 | 54100 |  |  | Study Module 11 | [18 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 54200 |  |  | Study Module 12 | [18 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 54300 |  |  | Study Module 13 | [18 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 54400 |  |  | Study Module 14 | [18 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 54500 |  |  | Study Module 15 | [18 empty] | 0
|  |  |  | 55000 |  | Study Modules 16-20
Not Started | 1.5 | 0 | 1.5 | 55100 |  |  | Study Module 16 | [18 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 55200 |  |  | Study Module 17 | [18 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 55300 |  |  | Study Module 18 | [18 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 55400 |  |  | Study Module 19 | [18 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 55500 |  |  | Study Module 20 | [18 empty] | 0
Not Started | 1 | 0 | 1 | 56000 |  | Questions Clarification for Midterm with Professor or TA | [19 empty] | 0
Not Started | 2 | 0 | 2 | 57000 |  | Final Revision for Midterm Exam | [19 empty] | 0
|  |  |  | 60000 | E2 - Study for Final Exam
Not Started | 1 | 0 | 1 | 61000 |  | Time-table plan to study for Final Exam | [19 empty] | 0
|  |  |  | 62000 |  | Study Modules 21-25
Not Started | 1.5 | 0 | 1.5 | 62100 |  |  | Study Module 21 | [18 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 62200 |  |  | Study Module 22 | [18 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 62300 |  |  | Study Module 23 | [18 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 62400 |  |  | Study Module 24 | [18 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 62500 |  |  | Study Module 25 | [18 empty] | 0
|  |  |  | 63000 |  | Study Modules 26-30
Not Started | 1.5 | 0 | 1.5 | 63100 |  |  | Study Module 26 | [18 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 63200 |  |  | Study Module 27 | [18 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 63300 |  |  | Study Module 28 | [18 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 63400 |  |  | Study Module 29 | [18 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 63500 |  |  | Study Module 30 | [18 empty] | 0
|  |  |  | 64000 |  | Study Modules 31-38
Not Started | 1.5 | 0 | 1.5 | 64100 |  |  | Study Module 31 | [18 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 64200 |  |  | Study Module 32 | [18 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 64300 |  |  | Study Module 33 | [18 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 64400 |  |  | Study Module 34 | [18 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 64500 |  |  | Study Module 35 | [18 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 64600 |  |  | Study Module 36 | [18 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 64700 |  |  | Study Module 37 | [18 empty] | 0
Not Started | 1.5 | 0 | 1.5 | 64700 |  |  | Study Module 38 | [18 empty] | 0
Not Started | 1 | 0 | 1 | 65000 |  | Questions Clarification for Finals with Professor or TA | [19 empty] | 0
Not Started | 2 | 0 | 2 | 66000 |  | Final Revision for Final Exam | [19 empty] | 0
|  |  |  | 89000 | Spare Task Rows - For use in Inserting New Tasks and Sub-Tasks
|  |  |  | 90000 | Spare Parent Task - Top Level
|  |  |  | 99000 |  | Spare Parent Task - Second Level
|  |  |  | 99900 |  |  | Spare Parent Task - Third Level
Not Started |  | 0 |  | 91000 |  | Spare Sub-Task - Second Level | [19 empty] | 0
Not Started |  | 0 |  | 99100 |  |  | Spare Sub-Task - Third Level | [18 empty] | 0
Not Started |  | 0 |  | 99910 |  |  |  | Spare Sub-Task - Fourth Level | [17 empty] | 0
Totals >> | 136.2 | 15.1 | 153 | Total Actual Hours Worked >> | [6 empty] | 15.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ^ | ^ | ^ | Cumulative Actual Hours (AC) >> | [6 empty] | 15.1 | 15.1 | 15.1 | 15.1 | 15.1 | 15.1 | 15.1 | 15.1 | 15.1 | 15.1 | 15.1 | 15.1 | 15.1 | 15.1 |  | 15.1
| Total Estimated Hours Remaining | Actual Hours So Far | Total Hours Originally Estimated | Estimated Hours Remaining (copy each week from total in column E) >> | [5 empty] | 153 | 2019-08-30: 136.2
| (copy to the right at the end of each week) | Should match Cumulative Actual Hours (AC) | Should match Cumulative Plan (PV) | [5 empty] | Week Number >> |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
|  |  |  | Hours Earned This Week (enter each week) >> | [6 empty] | 136.2 1: 15.1
|  |  |  | Cumulative Hours Earned (EV) >> | [6 empty] | 15.1 | 15.1 | 15.1 | 15.1 | 15.1 | 15.1 | 15.1 | 15.1 | 15.1 | 15.1 | 15.1 | 15.1 | 15.1 | 15.1
CPI >> | bar: 136.2 1 to 136.2 14
[9 empty] | SPI >> |  | 1.3817 | 0.69085 | 0.46057 | 0.34542 | 0.27634 | 0.23028 | 0.19739 | 0.17271 | 0.15352 | 0.13817 | 0.12561 | 0.11514 | 0.10628 | 0.098693
[11 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2018 Fall
Formulas:
Week Ending >> = [Week Ending >>, row above]+7